## Gantt Plan
Robot AI Automation Practice Project - 1 Hour per Week Gantt Plan
Start | 2026-07-06 | End | 2027-01-03 | Total hours | 26
Design principle | Simple block model + rough sizing + simulation evidence
Stage | Task | Simple weekly outcome | Start | End | Hours | Status | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
[8 empty] | 06/07 | 13/07 | 20/07 | 27/07 | 03/08 | 10/08 | 17/08 | 24/08 | 31/08 | 07/09 | 14/09 | 21/09 | 28/09 | 05/10 | 12/10 | 19/10 | 26/10 | 02/11 | 09/11 | 16/11 | 23/11 | 30/11 | 07/12 | 14/12 | 21/12 | 28/12
Stage 0 | Project setup | Create repo, folder structure, README, and one-page project aim | 2026-07-06 | 2026-07-12 | 1 | Not Started | Keep scope small: simple 2-link desktop arm or gantry concept.
Stage 1 | Requirements | Define what the demo robot must do, constraints, and success criteria | 2026-07-13 | 2026-07-19 | 1 | Not Started | Target: show capability, not build production robot.
Stage 1 | Simple robot concept | Sketch 2-3 options and select one low-complexity concept | 2026-07-20 | 2026-07-26 | 1 | Not Started | Recommended: 2-link planar arm or small 3-axis gantry.
Stage 1 | Parameter list | Create a short YAML/JSON parameter file for dimensions | 2026-07-27 | 2026-08-02 | 1 | Not Started | Only include 8-12 parameters.
Stage 2 | Basic CAD block model | Create simplified CAD using boxes/cylinders; no detailed manufacturing design | 2026-08-03 | 2026-08-09 | 1 | Not Started | Can be FreeCAD, Onshape, SolidWorks, or simple Python geometry.
Stage 2 | Parametric update test | Change one dimension from the parameter file and regenerate/update CAD | 2026-08-10 | 2026-08-16 | 1 | Not Started | Evidence: before/after screenshot.
Stage 2 | Mass assumptions | Estimate link masses with rough values; do not over-model | 2026-08-17 | 2026-08-23 | 1 | Not Started | Use simple assumed masses, lengths, payload.
Stage 3 | Worst-case torque sheet | Create a simple calculator for static torque at worst-case position | 2026-08-24 | 2026-08-30 | 1 | Not Started | Formula level: torque = force x distance.
Stage 3 | Motor shortlist | Pick 1-2 example motors/servos and check rough margin | 2026-08-31 | 2026-09-06 | 1 | Not Started | Do not buy parts unless needed.
Stage 3 | Sizing summary | Write one-page summary of assumptions, torque, margin, limitations | 2026-09-07 | 2026-09-13 | 1 | Not Started | This is the deliverable, not perfect engineering.
Stage 4 | URDF skeleton | Create simple URDF/Xacro with links and joints | 2026-09-14 | 2026-09-20 | 1 | Not Started | Use basic shapes first.
Stage 4 | ROS 2 package setup | Create robot_description and launch file structure | 2026-09-21 | 2026-09-27 | 1 | Not Started | Keep package minimal.
Stage 4 | Spawn in Gazebo | Load robot into Gazebo/Ignition with fixed world | 2026-09-28 | 2026-10-04 | 1 | Not Started | Screenshot proof is enough.
Stage 4 | Joint control test | Move one joint manually from ROS command or GUI | 2026-10-05 | 2026-10-11 | 1 | Not Started | Target: one reliable motion.
Stage 4 | Basic movement demo | Create a small scripted movement sequence | 2026-10-12 | 2026-10-18 | 1 | Not Started | Simple joint positions only.
Stage 5 | Agent command interface | Define safe functions the AI agent is allowed to call | 2026-10-19 | 2026-10-25 | 1 | Not Started | Example: move_joint, move_home, run_demo.
Stage 5 | Python tool wrapper | Build a Python wrapper around the movement commands | 2026-10-26 | 2026-11-01 | 1 | Not Started | Keep it deterministic and logged.
Stage 5 | AI prompt workflow | Write prompt that converts plain language into safe command calls | 2026-11-02 | 2026-11-08 | 1 | Not Started | No direct uncontrolled robot movement.
Stage 5 | Simulated AI control test | Run 2-3 example commands and capture results | 2026-11-09 | 2026-11-15 | 1 | Not Started | Evidence: screenshots or terminal logs.
Stage 6 | Future welding workflow map | Sketch future vision/welding concept at high level only | 2026-11-16 | 2026-11-22 | 1 | Not Started | No welding automation detail required now.
Stage 6 | Vision placeholder demo | Create placeholder script or diagram for camera detection pipeline | 2026-11-23 | 2026-11-29 | 1 | Not Started | Can be pseudo-code.
Stage 7 | GitHub cleanup | Clean folders, README, screenshots, and deliverables | 2026-11-30 | 2026-12-06 | 1 | Not Started | Make it employer-readable.
Stage 7 | Portfolio write-up | Write concise project page: problem, method, tools, result | 2026-12-07 | 2026-12-13 | 1 | Not Started | 1-2 pages max.
Stage 7 | Final demo video plan | Storyboard a 60-90 second demo video | 2026-12-14 | 2026-12-20 | 1 | Not Started | Screen recording is enough.
Stage 7 | Record final demo | Record or capture the working demo and screenshots | 2026-12-21 | 2026-12-27 | 1 | Not Started | Do not overproduce.
Stage 7 | Retrospective and next steps | Document lessons learned and next 3 possible improvements | 2026-12-28 | 2027-01-03 | 1 | Not Started | Close the loop clearly.

## Weekly Log
Week | Week starting | Planned task | Actual work completed | Time spent (hrs) | Evidence/link | Notes | Status
1 | 2026-07-06 | Project setup |  | 1 |  |  | Not Started
2 | 2026-07-13 | Requirements |  | 1 |  |  | Not Started
3 | 2026-07-20 | Simple robot concept |  | 1 |  |  | Not Started
4 | 2026-07-27 | Parameter list |  | 1 |  |  | Not Started
5 | 2026-08-03 | Basic CAD block model |  | 1 |  |  | Not Started
6 | 2026-08-10 | Parametric update test |  | 1 |  |  | Not Started
7 | 2026-08-17 | Mass assumptions |  | 1 |  |  | Not Started
8 | 2026-08-24 | Worst-case torque sheet |  | 1 |  |  | Not Started
9 | 2026-08-31 | Motor shortlist |  | 1 |  |  | Not Started
10 | 2026-09-07 | Sizing summary |  | 1 |  |  | Not Started
11 | 2026-09-14 | URDF skeleton |  | 1 |  |  | Not Started
12 | 2026-09-21 | ROS 2 package setup |  | 1 |  |  | Not Started
13 | 2026-09-28 | Spawn in Gazebo |  | 1 |  |  | Not Started
14 | 2026-10-05 | Joint control test |  | 1 |  |  | Not Started
15 | 2026-10-12 | Basic movement demo |  | 1 |  |  | Not Started
16 | 2026-10-19 | Agent command interface |  | 1 |  |  | Not Started
17 | 2026-10-26 | Python tool wrapper |  | 1 |  |  | Not Started
18 | 2026-11-02 | AI prompt workflow |  | 1 |  |  | Not Started
19 | 2026-11-09 | Simulated AI control test |  | 1 |  |  | Not Started
20 | 2026-11-16 | Future welding workflow map |  | 1 |  |  | Not Started
21 | 2026-11-23 | Vision placeholder demo |  | 1 |  |  | Not Started
22 | 2026-11-30 | GitHub cleanup |  | 1 |  |  | Not Started
23 | 2026-12-07 | Portfolio write-up |  | 1 |  |  | Not Started
24 | 2026-12-14 | Final demo video plan |  | 1 |  |  | Not Started
25 | 2026-12-21 | Record final demo |  | 1 |  |  | Not Started
26 | 2026-12-28 | Retrospective and next steps |  | 1 |  |  | Not Started

## Scope
Robot AI Automation Practice Project
Start date | 2026-07-06
Weekly time budget | 1 hour per week
Total planned duration | 26 weeks
Total planned effort | 26 hours
Project intent
Create a simple, evidence-based robotics workflow that keeps CAD, sizing, ROS 2/Gazebo, Python, and AI-agent skills active without becoming a large build.
Recommended simplified design
Use a 2-link planar arm or small 3-axis gantry. Use block geometry, simple torque calculations, and simulated movement only.
Success criteria
1. A small parameter-driven CAD concept exists.
2. A rough motor/torque sizing sheet exists.
3. A basic URDF/Gazebo model can spawn and move.
4. A safe Python command interface exists for AI-agent style control.
5. A short portfolio write-up and demo evidence exist.
Keep out of scope
Detailed manufacturing drawings, advanced dynamics, real welding automation, live hardware control, expensive purchased parts, and full autonomous welding.

## Summary
Project summary
Stage | Planned hours | Purpose
Stage 0 | 1 | Set up a clean project structure.
Stage 1 | 3 | Define a tiny robot concept and parameters.
Stage 2 | 3 | Create a basic parametric CAD concept.
Stage 3 | 3 | Complete simple static torque sizing.
Stage 4 | 5 | Build and move a ROS 2/Gazebo model.
Stage 5 | 4 | Create a safe AI-agent control interface.
Stage 6 | 2 | Map future vision/welding automation only at concept level.
Stage 7 | 5 | Package the work as a portfolio deliverable.